## Issues Status
S/N | Issues | Raised By | Issue Date | Date of Completion | Remarks | Status
1 | Travel advance should hit to finance | Sabin Raj Bhandari | 2017-04-18 |  | Development completed. Since this has to pass through synergy, waiting from Synergy team to revert (Rajesh) | QC
2 | Travel settlement is within 15 days | Sabin Raj Bhandari | 2017-04-18 |  | Development completed. Since this has to pass through synergy, waiting from Synergy team to revert (Rajesh) | QC
3 | HRIS Biomertics and Salary | Sabin Raj Bhandari | 2017-04-18 |  | Biometric Completed and Salary QC Rajesh to complete this yet. | ITN, WIP
4 | There is a practice of 1 or 2 hour relaxation on employee check-in/check-out time during Nepal bandh | Sabin Raj Bhandari | 2017-03-09 | 2017-06-02 | ITN to deliver, ITN Suggest to request for attendance for late or early hours in Nepal bandh to track the bandh time. To be tested at client location, will take time as we have to debug the unaticipated issues. Ukesh to work with Laxmi to close this. | On Process
5 | Leave earned by working on holidays can be compensated with substitute leave for employees level 8 and above. All employees below 8 will be compensated by OT | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver. JGI Business did not have clarity on it initially. Only on 5-Jun, JGI came up with this requirment with specifics. Now it is under development with ITN. | Payroll
6 | User Manual | Sabin Raj Bhandari | 2017-04-27 | 2017-06-11 | Preparing | On Process
7 | Attendance report |  |  |  | Further inputs from JGI needed, to performed on spot. QC being performed at ITN. Also ITN team expect someone from business to witness to make it bugfree,
10 | Baisakh Salary sheet to be generated from HRIS | ITN | End of Baisakh |  | ITN is ready for salary generation, awaiting JGI HR's response on when (we need employees attendance summary, OT, advance….) – data template to be collected from Rajesh…data provided | Payroll
12 | Day off in attendance report is showing "absent" | ITN | 2017-05-21 | 2017-06-02 | QC Remaining, Fixed by ITN team, will test run with JGI business and close. | On Process
14 | For few employee's OT is defaulted to certain hours to be taken care in HRIS | Sujan Pant | 2017-06-05 |  | In process by ITN team. Also expecting coordination with JGI HR to find a business logic | WIP
15 | Branch- As discussed earlier with Mr. Pramod,it was decided to change the Branch option.We have 5 factories which doesn’t need to be mentioned as Birgunj ,Bhairahawa etc. instead we can workout on the option for the employee who has been working outside the valley representing JGI. i.e. Marketing staffs,brand staffs and store staffs. | Laxmi Lama | 2017-05-05 |  | JGI prefer to have branch options by zone. Branch options: Zone 1, Zone 2, Zone 3, Zone 4, Zone 5, Zone 6, Valley1 and Valley 2. Laxmi needs to assign zones to each employee. In process by ITN. Ukesh to resolve with Laxmi. | WIP
16 | Department- two options are shown in dropdown of Department i.e. HR, Finance account | Laxmi Lama | 2017-05-05 |  | Ukesh to show Laxmiji from JGI before close. | WIP
17 | Training attendance and absentism list | Sujan Panta | 2017-05-05 |  | ITN has acknowledged this and will resolve on priority | WIP
18 | User role access report | Laxmi Lama | 2017-05-05 |  | ITN has acknowledged this and will resolve on priority | WIP
19 | In the admin Dashboard, details of list should appear when clicked at present, on leave….link is not working | Laxmi Lama | 2017-05-05 |  | For Admin it is completed. Pending self service | WIP
20 | Self service portal for Admin | Laxmi Lama | 2017-05-05 |  | ITN team is busy reviewing this requirement | WIP
21 | Expiry date of the contract and probation needs to be shown in dashboard | Laxmi Lama | 2017-05-05 |  | Early notification before 15 days is expected with date of appointment and expiry date. ITN Team is busy reviewing it. | WIP
22 | SAVE Button is very much needed in the employee data updating sections. It would be better if the button is nearer to NEXT button | Laxmi Lama | 2017-05-05 |  | Done | Complete
23 | SEARCH- The search option is not available in employee section.yes, we can search in usual way selecting the company and all but it would be user friendly if ERP could put an option just below the Name tag Jawalakhel Group of Industries .Actually during the data update process of each employee,we have to keep jumping to main section (EMPLOYEE ) time and again to search for another staffs so it’s kind of not easy | Laxmi Lama | 2017-05-05 |  | Yes, agreed with Development team | Complete
24 | Excel download- There is a problem in the downloaded data. Subject and content are not matching.please review | Laxmi Lama | 2017-05-05 |  | ITN Team is busy working on it. | WIP
25 | Shift of HDL has to be defined | Laxmi Lama | 2017-05-05 |  | JGI HR to define | Complete
26 | OT details has to be defined | Laxmi Lama | 2017-05-05 |  | JGI HR to provid the datas of OT; ITN is also busy on it. | WIP
27 | OT to be setup for the employee of level 7 & below | Laxmi Lama | 2017-05-05 |  | The employees up to level 7 shall be paid 1.5 times of the ordinary hourly rate of the basic salary, for every such additional hour worked. The employee shall have to mandatorily work for at least an hour for the purpose of being eligible to such additional remuneration. For easy understanding and for the purpose of calculation; payment of such additional remuneration shall be calculated on a half hourly basis (every 30 minutes). ITN is also busy on it. | WIP
29 | Grace time (early leave) and its late coming provision has to be defined | Laxmi Lama | 2017-05-05 |  | ITN to discuss with JGI for further clarity. | WIP
30 | Substitute leave has to be defined clearly.As per Mr. Ukesh work on holiday is just 3.5 or 4 hr which is equivalent to 1 day. | Laxmi Lama | 2017-05-05 |  | To be discussed with JGI HR and Sujanji. | WIP
31 | Please assist in finding out about Travel Notification and leave notification | Laxmi Lama | 2017-05-05 |  | Done | Complete
32 | Reporting Hierchay data upload | Sabin Raj Bhandari | 2017-04-18 |  | Template to be provided by Niraj | JGI, WIP
33 | HRIS access from Public net | Sabin Raj Bhandari | 2017-03-09 |  | It again a business call, if JGI want to get HRIS exposed into internet, ITN can do, but JGI need to understand the risks. | JGI Decision
34 | Data not representing correctly like same cell number…etc | Sabin Raj Bhandari | 2017-04-18 |  |  | JGI agreed to Employee themselves will be validating their datas as soon as the ERP post go-Live
35 | Details of miss Punched list | Sabin Raj Bhandari | 2017-04-18 |  | Ukesh to work with Laxmi on this. | Completed
36 | History Data uploda template | Sabin Raj Bhandari | 2017-04-18 |  | It was agreed that JGI HR will maintain this once the HRIS is live. | Completed
37 | Short Leave | Sabin Raj Bhandari | 2017-04-18 |  | To be managed using short leave, user can define and needs to be approved | Completed
38 | Travel code? | Sabin Raj Bhandari | 2017-04-18 |  | To be removed in travel request | Completed
39 | Subsitute is manadatory for travel | Sabin Raj Bhandari | 2017-04-18 |  |  | Completed
40 | Corner stone | Sabin Raj Bhandari | 2017-04-18 |  | This is the Performance Appriasal system being in use at the moment and JGI wants to continue with it for now | Closed
41 | On Employee self-service portal page he/she should be able to see the cumulative YTD leaves taken/absent/trainings… and same should also be available in HR report | Sabin Raj Bhandari | 2017-03-09 |  | ITN agreed to do necessary development/configuration on this | Completed
42 | Point raised by JGI HR was on how the employees with no PC/Laptops can access HRIS system | Sabin Raj Bhandari | 2017-03-09 |  | This is a business call, however ITN suggest to have a HR coordinator dedicated for such employees | Completed
43 | JGI HR raised a point on how to capture check-in and check-out time for late arrival/early leave due to some genuine official cause | Sabin Raj Bhandari | 2017-03-09 |  | ITN suggested to get this done through HR coordinator, need to have internal processes in place. | Completed
44 | Late check-in/early check-out is permitted as per policy for 2 days in a month, however, if this happens for more than prescribed time, employee will be trated as absent and he/she will have to manage this through normal leave processes if avilable. | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver | Completed
45 | Late check-in and early check-out on same day to be trated as absent | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver | Completed
46 | For every approvals JGI wants to have 2 level authorization | Sabin Raj Bhandari | 2017-03-09 |  | HRIS has got built-in features for 2 level authorization i.e. leave requests, advance request, travel request…etc all need 2 level approvals | Completed
47 | Job assignment: When an employee goes on leave/official travel, at the time of leave approval he/she himself/herself to delegate a person for his/her as a replacement. | Sabin Raj Bhandari | 2017-03-09 |  | ITN agrees to fix this. Will develop business logic as per our discussion i.e; the person on leave will have to recommend for his/her replacement and it will go for approval as per the hierarchy in the system | Completed
48 | JGI wants email notifications to approver by the system | Sabin Raj Bhandari | 2017-03-09 |  | ITN agrees to put this functionality in the system | Completed
49 | New hire or any other kind of company announcement to be flashed in the HRIS | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver, data entry complete, view remaining | Completed
50 | Someone got 3 days leave approved, however, he/she returns in 2 day…how to settle this in the system | Sabin Raj Bhandari | 2017-03-09 |  | ITN team to discuss internally and to revert to JGI | Completed
51 | Employee’s benefits like fuel/day, DA…etc depends on employee’s number of day present | Sabin Raj Bhandari | 2017-03-09 |  | ITN noted it and will work on business logic | Completed
52 | Work on holidays: In JGI there is a practice of treating a day as full working day for an employee who come and work on holidays (2 hr. work to be counted as half worked day, 4 hr.=1full worked day…) | Sabin Raj Bhandari | 2017-03-09 |  | ITN to work with business logic to accommodate this in the HRIS | Completed
53 | Handling resigned employees | Sabin Raj Bhandari | 2017-03-09 |  | ITN suggested this as normally needs to be handled by internal HR team like deactivating employee’s user id details, collecting all the allocated assets and entering into HR system, generating clearance letter…HR have to have an internal process in place | Completed
54 | JGI wants to attach all company provided gadgets with employee record | Sabin Raj Bhandari | 2017-03-09 |  | ITN informed that this is in-built in the system. | Completed
55 | JGI wants to have an option to gather online bio-data (self-service portal for all aspiring candidate) | Sabin Raj Bhandari | 2017-03-09 |  | ITN suggested that it won’t work unless HRIS is exposed to internet. However ITN to explore option to integrate current JGI website with HRIS with pros and cons. Please note that this involves major development work which will attract cost to JGI and in the interest of project timelines it is suggested to go for this change post go-live. | Post go -live, will incorporate feautures to capture applicant details + CV upload to synergy
56 | For new joiner: all facilities like leave/holidays entitlements to be set in the HRIS | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver | Completed
57 | Data accuracy assurance for Master data | Sabin Raj Bhandari | 2017-03-09 |  | ITN agrees and ensure for data consistance in Master Data, however, in reporting and any other form of presentation certain kind of error/bugs may be expected on which ITN will fix it. | JGI suggested to get this validated by employee themselves using self-service portal
58 | Company wise position not require in position setup. It is same for all | Sabin Raj Bhandari | 2017-04-27 |  |  | Completed
59 | Job history start date manually input can't work in Nepali calendar | Sabin Raj Bhandari | 2017-04-27 |  |  | Completed
60 | History search list link to employee. | Sabin Raj Bhandari | 2017-04-27 |  |  | Completed
61 | Need employee History link in employee setup. | Sabin Raj Bhandari | 2017-04-27 |  |  | Completed
62 | Managed Dashboard | Sabin Raj Bhandari | 2017-04-27 |  |  | Completed
63 | 1-May, we were supposed update JGI server with updated HRIS |  |  |  | We received revised data on 1-May; shofted to 4-May | Completed
64 | Provide user id and password for JGI employees by 1-May |  |  |  | Shifted to 4-May | Completed
65 | OT Management (OT request/approval processes) |  |  |  | To be completed internally by development team by 2-May | JGI to appoint a coordinator and get this resolved internally
66 | Asset management |  |  |  | Internally fixed by 4-May, on QC | Completed
67 | Collect revised data from JGI HR | JGI HR | 2017-05-01 |  | Received on 2-May | Completed
68 | Update JGI server | ITN | 2017-05-04 |  | Complete | Completed
69 | Asset management | ITN | 2017-05-05 |  | Development completed, to be put on QC on 11-May. | Completed
70 | Attendance device to be put into production | ITN | 2017-05-08 |  | Test complete, to be put on production on 12-May | Completed
71 | Data not in proper hierchy, detaIls given Ukesh (approver/reccomendor not in order) | ITN | 2017-05-09 |  | Hierarchy data to be prepared by JGI HR, training to be provided by ITN as per JGI HR convenient | Completed
72 | DoB is also found mistake for 4-5 users | ITN | 2017-05-09 |  | Could be data mismatch, need to manually adjust by JGI HR as verification yet to be done by JGI team | Agreed with JGI, employee to do themselves
73 | Attendance report with filters and pagination is not working | ITN | 2017-05-21 |  | done | Completed
74 | Dashboard present and other data verification | ITN | 2017-05-21 |  | QC remaining | Completed
75 | Data not representing correctly- This problem still exists in ERP, random data checking has been done for this but ERP team should assist in this part again | Laxmi Lama |  |  | JGI agreed to get this correction done from employees themselves | Completed