## Issues Status
S/N | Issues | Raised By | Issue Date | Date of Completion | Remarks | Remarks from ITN | Remarks from Laxmi
39 | Late check-in/early check-out is permitted as per policy for 2 days in a month, however, if this happens for more than prescribed time, employee will be trated as absent and he/she will have to manage this through normal leave processes if avilable. | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver | Complete
40 | Late check-in and early check-out on same day to be trated as absent | Sabin Raj Bhandari | 2017-03-09 |  | ITN to deliver | WIP - Verification pending
43 | JGI wants email notifications to approver by the system | Sabin Raj Bhandari | 2017-03-09 |  | ITN agrees to put this functionality in the system | WIP - Verification pending
52 | Managed Dashboard | Sabin Raj Bhandari | 2017-04-27 |  |  | WIP - Verification pending